## Sheet1
Tasks | Tables | Expected Start Date | Start Date | End Date | Status | Form Load | Help File | Save | Date | Teacher's Remarks
Goods Receive Note | GRN, GRNDetail, Item_Sec, Ledger | 2014-10-17
Sale GateOutward | Sale, SaleDetail, Item_Sec, Ledger | 2014-10-17
Stock Level Max | StockLevel, StockLevelDetail | 2014-10-17 | 2014-10-18 | 2014-10-18 | Done | Working | Done | Yes But ! Issue to be Checked
GRN Return | GRNRet, GRNRetDetail, Item_Sec, Ledger | 2014-10-17
Claim Contractor Charges | ClaimCont, ClaimContDet | 2014-10-18
Account Description | Heads | 2014-10-23 | 2014-10-23 | 2014-10-23 | Progress | Working | Done | Not saved yet
Customer Description | Customer, Heads | 2014-10-18 | 2014-10-23 | 2014-10-23 | Progress | Working | Done | Not saved yet
Vendor Description | Vendor, Heads | 2014-10-20 | 2014-10-23 | 2014-10-23 | Progress | Working | Done | Not saved yet
Production Process | ProdProc, ProdProcDetail, ProdProcSortment | 2014-10-20
Production Formula | ProdFormula, ProdFormulaDetail | 2014-10-20
Production Progress (Dept.) | ProdProcBatch, ProdProcBatchDetail, ProdProcBatchOrd, Item_Sec | 2014-10-22
Production Progress (Dept.) 2nd | ProdProcBatch, ProdProcBatchDetail, ProdProcBatchOrd, Item_Sec | 2014-10-22
Contractor Capacity | ContCap | 2014-10-22